## Gantt
Activity		Weeks					2 backend + 2 frontend + 1 native
#	Activity description	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16
1	Database structure
1.1	- E/R diagram
1.2	- Cloud Storage setup
1.3	- RDBMS setup
2	Web server
2.1	- API implementation
2.2	- Server application setup
2.3	- Reverse proxy setup
3	Web app
3.1	- UX design
3.2	- UI design
3.3	- Graphics
3.4	- Front end implementation
4	Native app
4.1	- Web app porting
4.2	- Native system integrations